## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sagari S A | 2026-02-08 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2026-02-09 | Closed | Issue resolved and validated with sample programs
2 | Sagari S A | 2026-02-09 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2026-02-11 | Closed | Style detection accuracy improved
3 | Sagari S A | 2026-02-16 | Syntax errors were not properly displayed for invalid code | Sprint 2 | Self | Logical | Enhanced error handling and improved message display | 2026-02-17 | Closed | Error messages are now user-friendly
4 | Sagari S A | 2026-02-18 | Undefined variables not detected in nested scopes | Sprint 2 | Self | Logical | Updated variable tracking logic for better scope handling | 2026-02-19 | Closed | Improved detection accuracy
5 | Sagari S A | 2026-03-03 | Some PEP 8 rules were missed during validation | Sprint 3 | Self | Standards | Expanded rule set and refined validation logic | 2026-03-04 | Closed | Coverage of style checks increased
6 | Sagari S A | 2026-03-05 | AI suggestions were not relevant for certain code inputs | Sprint 3 | Self | Logical | Tuned prompts and improved integration with AI model | 2026-03-06 | Closed | Suggestions became more accurate
7 | Sagari S A | 2026-03-17 | UI was not displaying categorized output properly | Sprint 4 | Self | User Interface | Redesigned layout to separate errors, warnings, and suggestions | 2026-03-18 | Closed | Improved user readability
8 | Sagari S A | 2026-03-19 | Multi-language support caused incorrect parsing for non-Python code | Sprint 4 | Self | Logical | Added language-specific conditions and validation checks | 2026-03-20 | Closed | System handles multiple languages better

## Sheet2
Logical
User Interface
Maintainability
Standards
Others